## Sheet1
Area | Component | Resources |  |  | Workshops & collaboration
|  | EP | CEU | Documentation | Presentation | Discovery | GAP analysis | Follow up | Comments
Editor | AT4LEX/XENAT | Cerro, Aristarchos | TBD |  | 2016-12-07 |  |  |  | diffing, spellchecking,...
Rendering | DM-XML | Thumatty | TBD |  | 2016-12-13 |  |  |  | Instantiation, validation, rendering and pre-fill
Rendering console | DM-XML console | Noviseth | TBD |  | 1st week of January
Storage | PURE-XML+EPS-PSL | Pagkos | Dekeyser, Palaikos | 2016-11-24 | 2016-11-29
Format | AkomaNtoso/XML4EP Lib | Specs/Pagkos | TBD
Transport protocol | eTrustX | TBD | BGeorge (EC) |  | Last week of Dec
Integration layer | EPS-TPL | TBD, Pagkos | TBD |  | TBD |  |  |  | TPL is EP specific, replicate only the functional role
Agenda
1. Identification of solution areas and domains (such as: user interface and editor, rendering, storage, ...)
2. Identification of resources and profiles per domain area
3. Definition of working method (joint technical sessions, prototyping, small workshops, ...)
4. Scheduling of the work
Note on G2: 2 days
Note on H2: 1 day