## Possible Trilogue Project Setup
id | Setup Type | Software at the EP | Software at the CEU | Common Exchange | Pros + | Cons -
1 | Separate development | EP developed editor, storage, rendering | CEU developed editor, storage, rendering | EP and CEU will separately develop integration to common platform (e-TrustX, IMMC, IFC) | - Clear budgetary and administrative boundaries - EP can benefit from leveraging of the e-Palriament developed platform (editor, storage and rendering) | - Delivery synchronisation risk
2 | CEU takes LegisWeb editor (LEOS) | EP developed editor, storage, rendering | CEU adopts LegisWeb editor, storage and rendering (LEOS) and integrates to CEU technical environment | EP and CEU will separately develop integration to common platform (e-TrustX, IMMC, IFC) | - Clear budgetary and administrative boundaries - EP can benefit from leveraging of the e-Palriament developed platform (editor, storage and rendering) | - Delivery synchronisation risk - Dependant on Commission delivery - Features synchronisation risk
3 | EP develops everything on joint business requirements and functional specifications | EP developed editor, storage, rendering | EP developed editor, CEU adapts and integrates in CEU technical environment for storage and rendering | EP will develop integration to common platform (e-TrustX, IMMC, IFC) | - Syncronisation of delivery - Early discovery of functional issues/gaps - Both parties actively participate in the business requirements and functional specifications - EP can benefit from leveraging of the e-Palriament developed platform (editor, storage, rendering and future transfer platform) | - Not clear budgetary and administrative boundaries risk - Joint definition of buisiness requirements and functional specifications may lenghten the approval process - Joint business requirements and functional specifications may be incompatible with EP or CEU constraints - Delay in solution acceptance due to integration challenges in CEU - Different roles, responsibilities and commitment (budget & resources) may lead to unbalanced business requirements (incomplete or exaggerated) - Complexity in solution design so that it accommodates integration of institution specific features
4 | EP and CEU develop together a common full-stack product (editor, storage, rendering and exchange) | Joint developed editor, storage and rendering | Joint developed editor, storage and rendering | Joint developed integration to common platform (e-TrustX, IMMC, IFC) | - Syncronisation of delivery based on the same product - Early discovery of functional issues/gaps - Both parties actively participate in the buisenss requirements and functional specifications - No specific integration developments needed | - No leveraging of the e-Palriament developed platform (storage and rendering) - High communication and coordination efforts - Complexity in solution design so that it accommodates integration of institution specific features
5 | EP and CEU develop together common components (editor and exchange) and separate integration of storage and rendering | Joint developed editors and EP developed storage and rendering | Joint developed editors and CEU developed storage and rendering | Joint developed integration to common platform (e-TrustX, IMMC, IFC) | - Early discovery of functional issues/gaps - Both parties actively participate in the business requirements and functional specifications - EP can benefit from leveraging of the e-Palriament developed platform (storage and rendering) | - High communicaiton and coordination - Complexity in solution design so that it accommodates integration of institution specific features - No reuse of e-Parliament editor and future transfer platform
6 | EP develops everything (discounted) | EP developed editor, storage, rendering | EP developed editor, storage and rendering on behalf of CEU | EP development and integration on behalf of CEU | - No dependancy to CEU project administration and decision making - Early discovery of functional issues/gaps | - More time and effort on EP - May have issues accessing CEU infrastructure and integrating applications - Buy-in and adoption of the solution from CEU - CEU acceptance of the final product
7 | CEU develops everything (discounted) | CEU developed editor, storage, rendering on behalf of EP | CEU developed editor, storage and rendering | CEU development and integration on behalf of EP | - No dependancy to EP project administration and decision making - Early discovery of functional issues/gaps | - More time and effort on CEU - May have issues accessing EP infrastructure and integrating applications - Buy-in and adoption of the solution from EP - EP acceptance of the final product