## Overview
Project Initial Risks Assessment | [10 empty] | Phase
Version 50 of 28/06/2013 |  |  |  | Last modifications: | 2013-12-19 11:09 | [5 empty] | Pre-Project
Definition
Realisation
Closure
Code
Name |  | TRILOEDIT
Comments
Description |  | A structured editor to manage the information and content negotiated between the Parliament and Council during Trilogue meetings
Project type |  | PMM Project
Current phase |  | Definition
|  | More than 65% |  | High Risks lifecycle
|  | 25% to 65% |  | Medium Risks lifecycle
|  | Less than 25% |  | Low Risks lifecycle
| The Project's lifecycle is: Medium Risks |  |  |  |  | Medium Risks
| Project IRA level: |  | 61.12% |  | Risks level by subgroup | 61.12% | PMM | BPM
| 1. Size |  |  |  | 52.38% |  | x
| 1.A | Project Estimation |  |  |  | 100% | x |  | =>To be tracked in the 'Dashboard'
| 1.B | Project Type |  |  |  | 0% | x
| 1.C | Project Team |  |  |  | 57.14% | x |  | =>To be tracked in the 'Dashboard'
| 2. Structure |  |  |  | 35.98% |  | x
| 2.A | Administration and Control |  |  |  | 0% | x
| 2.B | Project Team |  |  |  | 45.45% | x |  | =>To be tracked in the 'Dashboard'
| 2.C | Business Requirements |  |  |  | 62.5% | x |  | =>To be tracked in the 'Dashboard'
| 3. Technology |  |  |  | 95% |  | x
| 3.A | Technical Requirements |  |  |  | 90% | x |  | =>To be tracked in the 'Dashboard'
| 3.B | Security |  |  |  | 100% | x |  | =>To be tracked in the 'Dashboard'
|  |  | Scrum page | [6 empty] | Scrum lifecycle
To check if you could apply the Scrum lifecycle, please: 1/- Check all the IRA criteria 2/- Click on the "Scrum pre-requisites" button (on left) 3/- If IRA criteria are OK, the 'Scrum tab' will be open 4/- Check the Scrum criteria 5/- Check if all the IRA and Scrum criteria are OK to apply the Scrum lifecycle
IRA criteria are not fulfilled to apply SCRUM for the project
Project
Overall Risks view
Check Scrum pre-requisites
Scrum
Note on E19: Precise here the phase concerning by this assessment.

## 1. Size
1. Size
Current phase: Definition |  |  |  | Answer |  | Comments | PMM | BPM
1.A | Project Estimation |  |  | 100% | 30 |  | x
1.A.1 | What is the estimated total budget for the project? | a. | Less than 50 000€ | D | 15 |  | x
|  | b. | 50 000€ to 100 000€ |  |  |  | x
|  | c. | 100 000€ to 500 000€ |  |  |  | x
|  | d. | More than 500 000€ |  |  |  | x
1.A.2 | What is the estimated total workload for the project? | a. | Less than 100 man-day (m-d) | D | 15 |  | x
|  | b. | 100 m-d to 200 m-d |  |  |  | x
|  | c. | 200 m-d to 1 000 m-d |  |  |  | x
|  | d. | More than 1 000 m-d |  |  |  | x
1.B | Project Type |  |  | 0% | 0 |  | x
1.B.1 | The type of your project is: | a. | An IT development or an enhancement | A | 0 |  | x
|  | b. | A project of migration |  |  |  | x
|  | c. | A project of infrastructure |  |  |  | x
|  | d. | Other |  |  |  | x
1.C | Project Team |  |  | 57.14% | 20 |  | x
1.C.1 | What is the Project team experience (type of project / business / technical skills, etc.)? | a. | Very deep | C | 10 |  | x
|  | b. | Adequate |  |  |  | x
|  | c. | Limited |  |  |  | x
|  | d. | Not applicable |  |  |  | x
1.C.2 | Is a project Sponsor identified? | a. | Yes | A | 0 |  | x
|  | b. | No |  |  |  | x
1.C.3 | Who are the end users (target) of the project? | a. | EP Staff | A | 0 | EP and Council | x
|  | b. | Citizen |  |  |  | x
|  | c. | EP Members (MEP) |  |  |  | x
1.C.4 | How many DGs or Institutions are involved? | a. | One | C | 10 | EP: DG PRES, DG IPOL, DG ITEC Council: DQL | x
|  | b. | Between 1 and 3 |  |  |  | x
|  | c. | More than 3 |  |  |  | x

## 2. Structure
2. Structure
Current phase: Definition |  |  |  | Answer |  | Comments | PMM | BPM
2.A | Administration and Control |  |  | 0% | 0 |  | x
2.A.1 | Has a project management method been established for the project? | a. | PMM4EP | A | 0 |  | x
|  | b. | Other development method in addition to PMM4EP, to be justified in the 'Project Management Plan' |  |  |  | x
|  | c. | PMM4EP, first time used by the project team |  |  |  | x
2.A.2 | What is the level of availability of the Project Team? | a. | Adequate level of availability | A | 0 |  | x
|  | b. | Moderate level of availability |  |  |  | x
|  | c. | Low level of availability |  |  |  | x
2.B | Project Team |  |  | 45.45% | 25 |  | x
2.B.1 | A business analysis has previously been conducted and still relevant (Business Case and Business requirements collection delivered)? | a. | Yes | A | 0 |  | x
|  | b. | No |  |  |  | x
2.B.2 | Is there a Business Analyst in the Steering Committee? | a. | Yes | A | 0 |  | x
|  | b. | No |  |  |  | x
2.B.3 | Are some IT activities delegated to a third party (externalised, extra-muros)? | a. | No | B | 5 |  | x
|  | b. | Yes |  |  |  | x
2.B.4 | What is the experience of the EP Project Manager (MOE) with projects of a similar type/size? | a. | Demonstrated performance within the EP with similar projects | A | 0 |  | x
|  | b. | Demonstrated performance within the EP on different projects |  |  |  | x
|  | c. | Prior experience on similar projects but no experience at the EP |  |  |  | x
|  | d. | No experience |  |  |  | x
2.B.5 | What is the MOE Project team’s functional knowledge of the client's business? | a. | Excellent | C | 10 |  | x
|  | b. | Good |  |  |  | x
|  | c. | Fair |  |  |  | x
|  | d. | Poor |  |  |  | x
2.B.6 | To what degree will the client depend on an external staff to manage the project (requirements, documents, etc.)? | a. | Minimal dependence | C | 10 |  | x
|  | b. | Moderate dependence |  |  |  | x
|  | c. | High dependence |  |  |  | x
2.C | Business Requirements |  |  | 62.5% | 25 |  | x
2.C.1 | What is the percentage of modified or added functions by the new application? | a. | < 25% | C | 10 |  | x
|  | b. | 26-50% |  |  |  | x
|  | c. | > 51 |  |  |  | x
2.C.2 | How well known/defined are the needs of the project? | a. | Well known and defined | B | 5 |  | x
|  | b. | General understanding |  |  |  | x
|  | c. | Not well known/defined |  |  |  | x
2.C.3 | What is the probability of change in the project (scope, time and cost)? | a. | To a minimal degree (or not at all) | B | 5 |  | x
|  | b. | To a moderate degree |  |  |  | x
|  | c. | To a large degree |  |  |  | x
2.C.4 | To what degree will the result of the project impact normal operations and organization (change management)? | a. | Low | B | 5 |  | x
|  | b. | Moderate |  |  |  | x
|  | c. | High |  |  |  | x

## 3. Technology
3. Technology
Current phase: Definition |  |  |  | Answer |  | Comments | PMM | BPM
3.A | Technical Requirements |  |  | 90% | 45 |  | x
3.A.1 | How experienced is the MOE Project Team with the technology being used? | a. | Very experienced | B | 5 |  | x
|  | b. | Moderately experienced |  |  |  | x
|  | c. | Slightly or not experienced |  |  |  | x
3.A.2 | The Network Access is: | a. | Internal | C | 10 |  | x
|  | b. | External (DMZ) |  |  |  | x
|  | c. | Secure external (VPN) |  |  |  | x
|  | d. | Not Applicable |  |  |  | x
3.A.3 | What is the anticipated complexity of the conversion/migration effort? | a. | No data conversion effort | D | 15 |  | x
|  | b. | Straightforward |  |  |  | x
|  | c. | Average |  |  |  | x
|  | d. | Complex |  |  |  | x
3.A.4 | What is the required level for the performance of the system (e.g., response time, availability, capacity)? | a. | Reasonable expectations | B | 5 |  | x
|  | b. | Stringent requirements |  |  |  | x
|  | c. | Not Applicable |  |  |  | x
3.A.5 | How many different systems must be interfaced? | a. | None | C | 10 |  | x
|  | b. | 1 to 3 |  |  |  | x
|  | c. | More than 3 |  |  |  | x
3.B | Security |  |  | 100% | 25 |  | x
3.B.1 | How important are the security/privacy considerations to the new system? | a. | Limited importance | C | 10 |  | x
|  | b. | Moderate importance |  |  |  | x
|  | c. | Extreme importance |  |  |  | x
3.B.2 | What is the level of sensitivity of the data? | a. | Not sensitive | D | 15 |  | x
|  | b. | Low |  |  |  | x
|  | c. | Medium |  |  |  | x
|  | d. | High |  |  |  | x
|  | e. | Not Applicable |  |  |  | x

## Scrum_Pre-requisites (hidden)
4. Scrum - Pre-requisites
| Current phase: Definition | Answer | Comments
4.A | Pre-requisites
4.A.1 | Business Requirements are validated by the official Business representative (MOA Project Owner) |  |  | Please respond
4.A.2 | The Project must be developed in compliance with the EP IT environment and EP constraints |  |  | Please respond
4.A.3 | The Product Owner (Business representative) must be appointed at the inception of the project |  |  | Please respond
4.A.4 | The Product Owner must be available with the decision power regarding the Business side of the project |  |  | Please respond
4.A.5 | The whole Team (MOA and MOE) must be completely dedicated to the project with a real involvement and with a strong collaboration |  |  | Please respond
4.A.6 | Testing policy (similar to PMM4EP Master Test Plan) must be described in the Scrum dashboard |  |  | Please respond
4.A.7 | Some PMM4EP templates are used as Agile deliverables ('Initial Risks Assessment", "Charter Scope & Management Plan", "Technical Architecture Document", "Change requests", "Acceptance Report", "Project review") |  |  | Please respond
4.A.8 | People in the project must have a good knowledge of Agile values and practices |  |  | Please respond
4.A.9 | The Product must be delivered by an iterative and incremental process |  |  | Please respond
4.A.10 | Tools and automation: the Scrum process has to be supported according to the EP Foundry tools (see STANDARDS Unit website) Tools and Automation are available and operational |  |  | Please respond
0
10

## DB (hidden)
Parameters
[7 empty] | 270 | [9 empty] | 270
Group weightening |  |  | Group and subgroups weightening |  |  |  |  | Subgroup |  | Q # | Answer |  | Weight | Factor |  | Result | MAX |  | Option Tables |  |  |  |  | Scrum citeria | [8 empty] | Criteria validated | Not blank | Criteria validated and not blank
Group | WeightPMM |  | Group | Subgroup |  | WeightPMM | Max | 1.A | Project Estimation | 1.A.1 | A | 1 | 0 | 5 | 1.A.11 | 0 | 15 |  | 5 | 4 | 3 | 2 |  | 1.C | Project Team | 1.C.1 | A | 1 | 0 | 5 | 1.C.11 | 0 | 1 | TRUE | 1
1. Size | 33.33% |  | Size | 1.A | Project Estimation | 28% | 30 | 1.A | Project Estimation | 1.A.1 | B | 2 | 1 | 5 | 1.A.12 | 5 |  |  | A | A | A | A |  | 1.C | Project Team | 1.C.1 | B | 2 | 1 | 5 | 1.C.12 | 5
2. Structure | 33.33% |  |  | 1.B | Project Type | 15% | 15 | 1.A | Project Estimation | 1.A.1 | C | 3 | 2 | 5 | 1.A.13 | 10 |  |  | B | B | B | B |  | 1.B | Project Type | 1.B.1 | A | 1 | 0 | 5 | 1.B.11 | 0 | 0 | TRUE | 0
3. Technology | 33.33% |  | 100% | 1.C | Project Team | 57% | 35 | 1.A | Project Estimation | 1.A.1 | D | 4 | 3 | 5 | 1.A.14 | 15 |  |  | C | C | C |  |  | 1.C | Project Team | 1.C.2 | A | 1 | 0 | 5 | 1.C.21 | 0 | 0 | TRUE | 0
Total | 100% |  | Structure | 2.A | Administration and Control | 17% | 20 | 1.A | Project Estimation | 1.A.2 | A | 1 | 0 | 5 | 1.A.21 | 0 | 15 |  | D | D |  |  |  | 1.C | Project Team | 1.C.4 | A | 1 | 0 | 5 | 1.C.41 | 0 | 1 | TRUE | 1
|  |  |  | 2.B | Project Team | 50% | 55 | 1.A | Project Estimation | 1.A.2 | B | 2 | 1 | 5 | 1.A.22 | 5 |  |  | E |  |  |  |  | 2.B | Project Team | 2.B.1 | A | 1 | 0 | 5 | 2.B.11 | 0 | 0 | TRUE | 0
|  |  | 100% | 2.C | Business Requirements | 33% | 40 | 1.A | Project Estimation | 1.A.2 | C | 3 | 2 | 5 | 1.A.23 | 10 | [7 empty] | 2.B | Project Team | 2.B.2 | A | 1 | 0 | 5 | 2.B.21 | 0 | 0 | TRUE | 0
Cycle |  |  | Technology | 3.A | Technical Requirements | 71% | 50 | 1.A | Project Estimation | 1.A.2 | D | 4 | 3 | 5 | 1.A.24 | 15 | [14 empty] | IRA level | 61.12% | 1 | TRUE | 1
BPM Project |  |  | 100% | 3.B | Security | 29% | 25 | 1.B | Project Type | 1.B.1 | A | 1 | 0 | 5 | 1.B.11 | 0 | 15 |  | Option Values
PMM Project | [7 empty] | 1.B | Project Type | 1.B.1 | B | 2 | 1 | 5 | 1.B.12 | 5 |  |  |  | 0 | [11 empty] | Criteria not validated | 3
[8 empty] | 1.B | Project Type | 1.B.1 | C | 3 | 2 | 5 | 1.B.13 | 10 |  |  | A | 1 | [11 empty] | SCRUM lifecycle is possible | No
First time | [7 empty] | 1.B | Project Type | 1.B.1 | D | 4 | 3 | 5 | 1.B.14 | 15 |  |  | B | 2
Yes | [7 empty] | 1.C | Project Team | 1.C.1 | A | 1 | 0 | 5 | 1.C.11 | 0 | 10 |  | C | 3
[8 empty] | 1.C | Project Team | 1.C.1 | B | 2 | 1 | 5 | 1.C.12 | 5 |  |  | D | 4
Phase | [7 empty] | 1.C | Project Team | 1.C.1 | C | 3 | 2 | 5 | 1.C.13 | 10 |  |  | E | 5
Pre-Project | [7 empty] | 1.C | Project Team | 1.C.1 | D | 4 | 0 | 5 | 1.C.14 | 0 |  | Not applicable
Definition | [7 empty] | 1.C | Project Team | 1.C.2 | A | 1 | 0 | 5 | 1.C.21 | 0 | 5
[8 empty] | 1.C | Project Team | 1.C.2 | B | 2 | 1 | 5 | 1.C.22 | 5 |  |  |  |  | YesNo
All cells completed | [7 empty] | 1.C | Project Team | 1.C.3 | A | 1 | 0 | 5 | 1.C.31 | 0 | 10 |  |  |  | Yes
1.A Project Estimation | 2 | 0 | Yes |  |  |  |  | 1.C | Project Team | 1.C.3 | B | 2 | 1 | 5 | 1.C.32 | 5 |  |  |  |  | No
1.B Project Type | 1 | 0 | Yes |  |  |  |  | 1.C | Project Team | 1.C.3 | C | 3 | 2 | 5 | 1.C.33 | 10
1.C Project Team | 4 | 0 | Yes |  |  |  |  | 1.C | Project Team | 1.C.4 | A | 1 | 0 | 5 | 1.C.41 | 0 | 10
2.A Administration and Control | 2 | 0 | Yes |  |  |  |  | 1.C | Project Team | 1.C.4 | B | 2 | 1 | 5 | 1.C.42 | 5
2.B Project Team | 6 | 0 | Yes |  |  |  |  | 1.C | Project Team | 1.C.4 | C | 3 | 2 | 5 | 1.C.43 | 10
2.C Business Requirements | 4 | 0 | Yes |  |  |  |  | 2.A | Administration and Control | 2.A.1 | A | 1 | 0 | 5 | 2.A.11 | 0 | 10
3.A Technical Requirements | 5 | 0 | Yes |  |  |  |  | 2.A | Administration and Control | 2.A.1 | B | 2 | 1 | 5 | 2.A.12 | 5 | x
3.B Security | 2 | 0 | Yes |  |  |  |  | 2.A | Administration and Control | 2.A.1 | C | 3 | 2 | 5 | 2.A.13 | 10 | x
[8 empty] | 2.A | Administration and Control | 2.A.2 | A | 1 | 0 | 5 | 2.A.21 | 0 | 10
[8 empty] | 2.A | Administration and Control | 2.A.2 | B | 2 | 1 | 5 | 2.A.22 | 5 | x
[8 empty] | 2.A | Administration and Control | 2.A.2 | C | 3 | 2 | 5 | 2.A.23 | 10 | x
[8 empty] | 2.B | Project Team | 2.B.1 | A | 1 | 0 | 5 | 2.B.11 | 0 | 5
[8 empty] | 2.B | Project Team | 2.B.1 | B | 2 | 1 | 5 | 2.B.12 | 5
[8 empty] | 2.B | Project Team | 2.B.2 | A | 1 | 0 | 5 | 2.B.21 | 0 | 5
[8 empty] | 2.B | Project Team | 2.B.2 | B | 2 | 1 | 5 | 2.B.22 | 5
[8 empty] | 2.B | Project Team | 2.B.3 | A | 1 | 0 | 5 | 2.B.31 | 0 | 5
[8 empty] | 2.B | Project Team | 2.B.3 | B | 2 | 1 | 5 | 2.B.32 | 5
[8 empty] | 2.B | Project Team | 2.B.4 | A | 1 | 0 | 5 | 2.B.41 | 0 | 15
[8 empty] | 2.B | Project Team | 2.B.4 | B | 2 | 1 | 5 | 2.B.42 | 5
[8 empty] | 2.B | Project Team | 2.B.4 | C | 3 | 2 | 5 | 2.B.43 | 10
[8 empty] | 2.B | Project Team | 2.B.4 | D | 4 | 3 | 5 | 2.B.44 | 15
[8 empty] | 2.B | Project Team | 2.B.5 | A | 1 | 0 | 5 | 2.B.51 | 0 | 15
[8 empty] | 2.B | Project Team | 2.B.5 | B | 2 | 1 | 5 | 2.B.52 | 5
[8 empty] | 2.B | Project Team | 2.B.5 | C | 3 | 2 | 5 | 2.B.53 | 10
[8 empty] | 2.B | Project Team | 2.B.5 | D | 4 | 3 | 5 | 2.B.54 | 15
[8 empty] | 2.B | Project Team | 2.B.6 | A | 1 | 0 | 5 | 2.B.61 | 0 | 10
[8 empty] | 2.B | Project Team | 2.B.6 | B | 2 | 1 | 5 | 2.B.62 | 5 | x
[8 empty] | 2.B | Project Team | 2.B.6 | C | 3 | 2 | 5 | 2.B.63 | 10 | x
[8 empty] | 2.C | Business Requirements | 2.C.1 | A | 1 | 0 | 5 | 2.C.11 | 0 | 10
[8 empty] | 2.C | Business Requirements | 2.C.1 | B | 2 | 1 | 5 | 2.C.12 | 5 | x
[8 empty] | 2.C | Business Requirements | 2.C.1 | C | 3 | 2 | 5 | 2.C.13 | 10 | x
[8 empty] | 2.C | Business Requirements | 2.C.2 | A | 1 | 0 | 5 | 2.C.21 | 0 | 10
[8 empty] | 2.C | Business Requirements | 2.C.2 | B | 2 | 1 | 5 | 2.C.22 | 5 | x
[8 empty] | 2.C | Business Requirements | 2.C.2 | C | 3 | 2 | 5 | 2.C.23 | 10 | x
[8 empty] | 2.C | Business Requirements | 2.C.3 | A | 1 | 0 | 5 | 2.C.31 | 0 | 10
[8 empty] | 2.C | Business Requirements | 2.C.3 | B | 2 | 1 | 5 | 2.C.32 | 5 | x
[8 empty] | 2.C | Business Requirements | 2.C.3 | C | 3 | 2 | 5 | 2.C.33 | 10 | x
[8 empty] | 2.C | Business Requirements | 2.C.4 | A | 1 | 0 | 5 | 2.C.41 | 0 | 10
[8 empty] | 2.C | Business Requirements | 2.C.4 | B | 2 | 1 | 5 | 2.C.42 | 5 | x
[8 empty] | 2.C | Business Requirements | 2.C.4 | C | 3 | 2 | 5 | 2.C.43 | 10 | x
[8 empty] | 3.A | Technical Requirements | 3.A.1 | A | 1 | 0 | 5 | 3.A.11 | 0 | 10 |  |  |  |  | 10
[8 empty] | 3.A | Technical Requirements | 3.A.1 | B | 2 | 1 | 5 | 3.A.12 | 5 | x
[8 empty] | 3.A | Technical Requirements | 3.A.1 | C | 3 | 2 | 5 | 3.A.13 | 10 | x
[8 empty] | 3.A | Technical Requirements | 3.A.2 | A | 1 | 0 | 5 | 3.A.21 | 0 | 10 |  |  |  |  | 10
[8 empty] | 3.A | Technical Requirements | 3.A.2 | B | 2 | 1 | 5 | 3.A.22 | 5
[8 empty] | 3.A | Technical Requirements | 3.A.2 | C | 3 | 2 | 5 | 3.A.23 | 10
[8 empty] | 3.A | Technical Requirements | 3.A.2 | D | 4 | 0 | 5 | 3.A.24 | 0 |  | Not applicable
[8 empty] | 3.A | Technical Requirements | 3.A.3 | A | 1 | 0 | 5 | 3.A.31 | 0 | 15 |  |  |  |  | 15
[8 empty] | 3.A | Technical Requirements | 3.A.3 | B | 2 | 1 | 5 | 3.A.32 | 5 | x
[8 empty] | 3.A | Technical Requirements | 3.A.3 | C | 3 | 2 | 5 | 3.A.33 | 10 | x
[8 empty] | 3.A | Technical Requirements | 3.A.3 | D | 4 | 3 | 5 | 3.A.34 | 15 | x
[8 empty] | 3.A | Technical Requirements | 3.A.4 | A | 1 | 0 | 5 | 3.A.41 | 0 | 5 |  |  |  |  | 5
[8 empty] | 3.A | Technical Requirements | 3.A.4 | B | 2 | 1 | 5 | 3.A.42 | 5
[8 empty] | 3.A | Technical Requirements | 3.A.4 | D | 3 | 0 | 5 | 3.A.43 | 0 |  | Not applicable
[8 empty] | 3.A | Technical Requirements | 3.A.5 | A | 1 | 0 | 5 | 3.A.51 | 0 | 10 |  |  |  |  | 10
[8 empty] | 3.A | Technical Requirements | 3.A.5 | B | 2 | 1 | 5 | 3.A.52 | 5 | [6 empty] | 50
[8 empty] | 3.A | Technical Requirements | 3.A.5 | C | 3 | 2 | 5 | 3.A.53 | 10
[8 empty] | 3.B | Security | 3.B.1 | A | 1 | 0 | 5 | 3.B.11 | 0 | 10
[8 empty] | 3.B | Security | 3.B.1 | B | 2 | 1 | 5 | 3.B.12 | 5 | x
[8 empty] | 3.B | Security | 3.B.1 | C | 3 | 2 | 5 | 3.B.13 | 10 | x
[8 empty] | 3.B | Security | 3.B.2 | A | 1 | 0 | 5 | 3.B.21 | 0 | 15
[8 empty] | 3.B | Security | 3.B.2 | B | 2 | 1 | 5 | 3.B.22 | 5
[8 empty] | 3.B | Security | 3.B.2 | C | 3 | 2 | 5 | 3.B.23 | 10
[8 empty] | 3.B | Security | 3.B.2 | D | 4 | 3 | 5 | 3.B.24 | 15
[8 empty] | 3.B | Security | 3.B.2 | E | 5 | 0 | 5 | 3.B.25 | 0 |  | Not applicable
Note on T4: Dépend du choix défini dans overview et du type de la question (BPM ou PMM) > si ces deux conditions sont remplies alors le maximum est calculé